## Pending Tests
ID | Area | Market | Test | Why it is pending | Steps | Expected result | Environment | Depends on | Priority | Status | Job ID / Evidence | Tested on | Remarks
T01 | Master Data with Content | MNAO | en-CA companion locale - files present | New 2026-10-11: an en-US schedule also processes en-CA (masterdata.companion.locales). Built, not yet run. | 1. Put CA_EN-CA_<type>.xlsx files next to the en-US files in the MDM folder. 2. Schedule MNAO en-US with Master Data with Content. | MASTER_DATA_LOAD_REPORT lists en-CA rows; MASTER_DATA_CATEGORY_REPORT lists en_CA categories; en-CA MDM rows end with sync status Y; log shows 'companion locale en-CA processed too'. | MC Dev | MDM country CA / manual language en-CA active | High | Pending
T02 | Master Data with Content | MNAO | en-CA companion locale - no en-CA file | New 2026-10-11: a missing en-CA file must not fail the job. | Schedule MNAO en-US with Master Data with Content, MDM folder WITHOUT CA_EN-CA files. | No 'No master data file found' row for en-CA; log line 'companion locale en-CA :: no master data file'; en-CA rows already at N are sent to Kapture. | MC Dev | - | High | Pending
T03 | Schedule - Only content check | MNAO | Only content warning counts en-CA | New 2026-10-11: the check now covers the companion locale. | 1. Leave at least one en-CA MDM row at sync status N. 2. Schedule MNAO en-US with Only content. | Warning appears and names 'locale en-US, en-CA'. With no N rows in en-US / en-CA: no warning. | MC Dev | - | Medium | Pending
T04 | Conversion re-test | MC | MC conversion on the current dmtgt.war with Master Data with Content | 2026-10-10 category changes (DB mode, all-locales fill, last-row label rule) re-tested for MNAO only. | Schedule MC ja-JP with Master Data with Content (e-WD / WM sample). | Categories written in DB mode (no Kapture login for categories); new categories present in all k_default_locales; no label UPDATED for keys Master Data Syncing already set; documents created/updated as before. | MC Dev | - | High | Pending
T05 | Conversion re-test | MME | MME conversion on the current dmtgt.war with Master Data with Content | Same as T04 - MME not re-tested since 2026-10-10. | Schedule MME (e.g. en-UK / de-DE) with Master Data with Content. | As T04 for the MME locale. | MC Dev | - | High | Pending
T06 | Schedule - Only content check | MC / MME | Only content warning per selected locale | Per-locale check verified for MNAO only (5694). | 1. Leave N rows in a locale that is NOT selected. 2. Schedule MC / MME with Only content for another locale. | No warning for rows of the other locale; warning when the selected locale has N rows, message shows the locale. | MC Dev | - | Medium | Pending
T07 | Conversion - ESI | MC | ESI category mapping end to end | Test esicat.txt used on MC Dev had 5-field lines (no ESI codes) - ESI path not proven for MC. | Run an MC job whose esicat.txt carries ESI codes (8 fields, e.g. 04¦¦041100¦¦00). | ESI TAXONOMY / MAPPED filled in the reports; documents tagged with the ESI categories in Kapture. | MC Dev | Business sample with ESI codes | Medium | Pending
T08 | Preview | MC | WD HTML_MC / HTML5 file documents in Preview | No sample content of that type so far. | Convert a WD HTML_MC / HTML5 item, open the Preview page. | Pages render with their own model folder; voltage / window.open links work. | MC Dev | Business sample | Low | Pending
T09 | Preview | All | PDF inline display in Chrome | Proven offline only. | Open a PDF document in the Preview page in Chrome. | PDF shows inline in the right pane. | MC Dev | - | Low | Pending
T10 | Conversion - WD | MME | WD voltage links resolve | 84 links unresolved in 5617 because their targets were not loaded. | Load NewM_CX-5_km/WM/FL0000/E-WZE-69P1_XML, re-run the WD item. | Voltage links resolve; no 'unresolved' lines for them. | MC Dev | Target content loaded | Low | Pending
T11 | Conversion - WM | MME | BT-50 WM full volume (5,214 docs) | Only partial volumes run so far. | Schedule the full BT-50 WM item. | Job completes; timings and failures in line with earlier runs. | MC Dev | - | Low | Pending
T12 | Conversion - WD | MME | window.js handling | No MME sample with window.js yet. | Run an MME item that carries window.js. | window.js copied to OKAssets with /content/library prefix (MC rule). | MC Dev | Business sample | Low | Pending
T13 | History | MME / MNAO | Late-day job visible in History | Date filter fix (9 h timestamp shift) verified for MC only. | Run an MME / MNAO job late in the day, filter History by today. | Job listed. | MC Dev | - | Low | Pending
T14 | File behaviour | All | Re-check file-based behaviour after Syncthing | rsync on /s3kapture brings deleted files back (preview.json, preview folders, reports, OKAssets). | After Infra moves to Syncthing: run a delete job and a publish. | Deleted preview docs stay gone from the earlier job's Preview page; report xlsx stay deleted after zipping; OKAssets deletes stay deleted. DB results unchanged (Delete counts, Kapture unpublished, preview_docs DELETED). | MC Dev | Infra: Syncthing live | Medium | Blocked
T15 | Automation (Facelift) | MC | IPM Facelift VIN Update end to end - Only Facelift | Built 2026-10-11: InfoManager replaced by Kapture (read latest article, swap only the VIN categories, update, publish). | 1. Put a ja_JP facelift Excel (11 columns) in Facelift_Content. 2. Validate Data, Identify, then select items and schedule with Only Facelift. | Impacted SM / OSM / WD docs found; in Kapture only the old VIN categories are replaced by the new ones (other categories, user groups, views, owner unchanged); gms3_vc_japan_vin_details rows carry the new VIN + carline / model names; processed / failed counts and reports correct. | MC Dev | - | High | Passed | MC Dev 5708 / 5715 | 2026-10-12 | ja-JP WD CX-5 (KM), 820 docs, 0 failures both runs (5708 Master Data with Facelift, 5715 Only Facelift); VINs swapped in Kapture + gms3_vc_japan_vin_details (user checked WD25070 / WD28673); no VIN manual type report for MC (5715).
T16 | Automation (Facelift) | MME | IPM Facelift VIN Update end to end - Only Facelift | As T15; MME view content table now lowercase (gms3_vc_mme_vin_dtl_<locale>). | As T15 with an MME locale (e.g. en_UK) in the Excel. | As T15 on gms3_vc_mme_vin_dtl_<locale>; gms3_mdm_vin_ml_mapping updated; MME VIN manual type mapping report in the zip. | MC Dev | - | High | Pending
T17 | Automation (Facelift) | MNAO | IPM Facelift VIN Update end to end - Only Facelift | As T15; legacy MNAO match kept (WMI / VDS / VIS, locale filter). | As T15 with an en-US row in the Excel. | As T15 on gms3_vc_vin_details (WMI / VDS / VIS of the matched rows replaced). | MC Dev | - | High | Pending
T18 | Automation (Facelift) | All | Abort from History + conversion regression | History abort of an automation job no longer clears gms3_dmt_el_gr_nm_dispord; Schedule.java dead code removed and its per-request fields moved to ThreadLocals (touches the conversion threads too). | 1. Start a conversion, then abort an automation job from History. 2. Run one normal conversion per market. | Automation job aborted; display-order staging of the running conversion untouched; conversions finish as before with the right user id on the schedule. | MC Dev | - | Medium | Pending
T19 | QA regression | MC | Full DMT regression on QA | DB changes applied on MC QA 2026-10-10 (Job 2 option 2); DMT app not yet tested there. | Conversion (Master Data with Content + Only content), Publish, Delete, Master Data Syncing, Meta Data Validation, Automation. | Same results as on MC Dev. | MC QA | dmtgt.war deployed on QA with QA properties | High | Pending
T20 | QA regression | MME | Full DMT regression on QA | As T19. | As T19. | As T19. | MC QA | As T19 | High | Pending
T21 | QA regression | MNAO | Full DMT regression on QA (incl. en-CA companion) | As T19. | As T19 + T01-T03. | As T19. | MC QA | As T19 | High | Pending
T22 | Automation (Facelift) | All | Facelift folder read - no upload | New 2026-10-11: every Excel of Facelift_Content (beside MDM) is read instead of an upload. | 1. No Facelift_Content folder / empty folder: open the IPM Facelift VIN Update page. 2. Two Excel files with mixed locales + an open Excel (~$ lock file) in the folder: Validate Data. | 1. 'No Excel file found' message, no Validate button. 2. Both files listed (lock file not), rows of both read and validated; messages name the file and row. | MC Dev | - | High | Passed | Local deploy (UI + validation) | 2026-10-11 | Validated by the user on the local dmtgt.war.
T23 | Automation (Facelift) | All | Validation errors | Validation now against MDM + Kapture (k_categories / k_default_locales) instead of OK_IM. | Excel with: a blank cell, an unknown locale, an OLD VIN missing in Kapture, an OLD VIN missing in MDM, a NEW VIN in neither MDM / Kapture nor the ALL_VIN file. Then one with more than 10 errors. | One error per case naming Kapture / MDM, row and file; Identify button not shown. More than 10 errors: text file link. | MC Dev | - | High | Passed | Local deploy (UI + validation) | 2026-10-11 | Validated by the user on the local dmtgt.war.
T24 | Automation (Facelift) | All | New VIN only in the ALL_VIN master data file | New 2026-10-11: a new VIN range missing in Kapture passes validation when the locale's ALL_VIN file carries it (D rows excluded). | 1. Excel row whose NEW VIN is only in the ALL_VIN file: Validate, Identify. 2. Schedule with Only Facelift. 3. Same range marked D in the ALL_VIN file: Validate. | 1. Validation passes. 2. Refused with 'Only Facelift cannot be scheduled - n new VIN categories are not in Kapture yet'. 3. Validation error for the new VIN. | MC Dev | - | High | Pending
T25 | Automation (Facelift) | All | Master Data with Facelift | New 2026-10-11: the master data of the item locales is loaded at the start of job B (like conversion); choice kept in dc_load_type. | Continue T24: schedule the same items with Master Data with Facelift. | Master data loaded first (new VIN category now in Kapture); documents updated with the new VIN and the refreshed model names; master data load / category reports inside the job zip; dc_load_type = MASTER_DATA_WITH_CONTENT. | MC Dev | T24 | High | Pending
T26 | Automation (Facelift) | All | Publish state kept | D1: a document whose latest version is Published is updated and published again; a draft stays a draft. | Include one document with a published latest version and one with a draft latest version in an item; run job B. | k_article: the published one has a new live version carrying the new VIN; the draft one has a new draft, not published. | MC Dev | - | High | Passed | MC Dev 5715 | 2026-10-12 | 54 published docs re-published, report version 4.0 (read back from k_article), vc_content_status Published; drafts stay Draft (e.g. WD28673 0.3).
T27 | Automation (Facelift) | All | Failed document keeps the old VIN | Order per batch: Kapture first, view content only for documents Kapture accepted. | Make one document fail in Kapture (e.g. locked / checked out by another user) and run job B. | That document reported with KAPEXP003 / KAPEXP004 and counted as failed; its view content rows keep the OLD VIN; the other documents of the batch updated normally. | MC Dev | - | Medium | Pending
T28 | Schedule page | All | Two users on the Schedule page at the same time | Schedule.java per-request fields (messages, server path, user id) were shared servlet fields - now ThreadLocals. | Two users (different iv-user) work on the Schedule page at the same time; each schedules a job. | Each sees their own messages; each schedule carries its own user id. | MC Dev | - | Medium | Pending
T29 | Regression | All | InfoManager removal - smoke of every screen | 2026-10-11: infomanager package, build-lib/infomanager and the IM properties removed (all dead code). | Deploy the new dmtgt.war; open every screen; run one Master Data Syncing and one Meta Data Validation. | No ClassNotFound / NoClassDefFound in the catalina log; screens and jobs work as before. | MC Dev | - | High | Pending
T30 | Schedule - Conversion Go | All | Facelift run confirmation before the conversion records are listed | New 2026-10-11: order with all three folders = MDM, then Facelift_Content (IPM Facelift VIN Update), then GMS3_Content. | 1. Excel in Facelift_Content: select conversion filters, click Go, answer No. 2. Click Go again, answer Yes. 3. No Excel in Facelift_Content (or no folder): click Go. | 1. Dialog 'Facelift Content found'; No = no records listed, nothing can be scheduled. 2. Records listed as before. 3. No dialog, records listed directly. | MC Dev | - | High | Passed | Local deploy (UI) | 2026-10-11 | Validated by the user on the local dmtgt.war.
T31 | Automation (Facelift) | All | Old VIN ranges made inactive in MDM after a successful job | New 2026-10-12: a successful job sets mdm_vin_flag = deleted (sync status cleared) for its old VIN ranges; Kapture untouched. | 1. Run a job that ends Success. 2. Run a job with at least one failed document. | 1. OLD_VIN_DEACTIVATION_REPORT.xlsx in the zip (DEACTIVATED, MDM locale shown); the old range no longer active in MDM; old VIN category still in Kapture. 2. No deactivation, no report; log 'the old VIN ranges stay active in MDM'. | MC Dev | - | High | Passed | MC Dev 5715 | 2026-10-12 | Old range KM___KMY___100001199999 deactivated in MDM (ja-JP, 1 row); OLD_VIN_DEACTIVATION_REPORT.xlsx in the zip; Kapture untouched.
T32 | Automation (Facelift) | All | Identification job after its items are scheduled - count, remark, View | New 2026-10-12: the count is kept (legacy reduced it to 0) with a remark naming the update job; View only while an item is left. | 1. Identify, schedule ALL its items in an update job, refresh the job list during and after the job. 2. Identify with 2+ items, schedule ONE, refresh. | 1. TOTAL DOCUMENTS unchanged; REMARKS '<n> documents (<locale> <channel> <model>) processed by MGSS_MDSYNC_...'; no View link. A View clicked on a stale page shows 'No item left to schedule...'. 2. View still shown, lists only the remaining item. | MC Dev | - | Medium | In Progress | MC Dev identification job 59 / 5715 | 2026-10-12 | Step 1 OK (user): count stayed 820, remark shown, no View link. Step 2 (schedule one of two items) not run yet.
T33 | Conversion - display order file | MC | delete.txt is ignored (not read as a display order file) | Fixed 2026-10-12: delete.txt is no longer used; the display order check compared the name with 'delete' only, so delete.txt was read as a display order file. Now: starts with d, ends with .txt, not delete.txt (Schedule screen + conversion). | 1. Put a delete.txt beside vin.txt / d01.txt in a facelift folder. 2. Go, select the row, Schedule; let the job finish. | Row accepted (no 'cannot be selected'); display order rows saved = d01.txt lines only; DISPLAY_ORDER / CD reports list d01.txt / CD00.txt only; delete.txt nowhere in reports; job Success. | MC Dev | - | Medium | Passed | MC Dev 5729 | 2026-10-12 | ja-JP NewM_familia_van_ncp WM FL0001 with delete.txt in the folder: scheduled without error; 2,778 display order rows saved = d01.txt lines exactly (CD 2,778 from CD00.txt); DISPLAY_ORDER + CD reports 11/11 SUCCESS, d01.txt / CD00.txt only; TRANSACTION 11 SUCCESS, VIEW_CONTENT 22 SUCCESS; delete.txt in no report; 0 ERROR lines; preview 11 docs; job Success.
T34 | Conversion - display order file | MME / MNAO | delete.txt is ignored (not read as a display order file) | Same fix in StartMMEConversionImpl / StartConversionMNAOImpl; run on MC only (T33). | As T33 with an MME and an MNAO item. | As T33. | MC Dev | - | Low | Pending
T35 | Settings page | All | Content Provision Guide + Download PDF | New 2026-10-12: 10-tab guide under the network path; PDF (cover + contents with page numbers, page footer) shipped in the war. | 1. Open Settings, click through all tabs, reload (last tab kept). 2. Click Download PDF. | Tabs switch, content readable; PDF downloads with contents, page numbers, links and bookmarks. | Local + MC Dev | - | Low | Passed | Local + MC Dev deploy | 2026-10-12 | Validated by the user on both deployments: guide tabs and PDF download (v2 with contents page numbers and footer).
T36 | Conversion - library paths sent to Kapture | MC / MME / MNAO | /content/ prefix on every /library/ path DMT sends to Kapture | New 2026-10-13 (same rule as Job 10): kapture.library.path.context=/content. KaptureArticleBuilder prefixes HTML5_UPLOAD_DIRECTORY, DJVU_FILE_LOCATION, OASIS_FILE_LOCATION, OEM_FILE_LOCATION and every src / href starting /library/ in the HTML (img, a, link, embed). DMT tables + preview keep /library/. | 1. Deploy the war with kapture.library.path.context=/content in application.properties. 2. Run one conversion per market: MC SM (with images + a PDF link), MME WD HTML5, MNAO WD HTML5 / DJVU (new layout), an OSM item, and an MC OEM item. 3. In Kapture open each document (or /latest-article) and check the path attributes and the img src / a href. 4. Open the documents in the Kapture viewer. | Every library path reads /content/library/MAZDA/...; WD MNAO paths keep .../<model>/<manual type>/<facelift>/<material>/...; nothing is /content/content/; links to other documents (index?page=...) unchanged; images, PDFs and HTML5 / DJVU open. | MC Dev | - | High | Pending
T37 | Conversion - display order / CD cleanup | MC | Documents no longer in the display order (or CD file) lose their view content (CD data) | New 2026-10-13/14: for the vin.txt material folders of the item, ACTIVE documents the display order files do not list lose their view content (CD: CD data). A document converted again lost it already in the document step - recorded (ClearedDisplayData) so it is reported too. Report: new OPERATION column (INSERT / DELETE). Preview NOT changed. | 1. Run the familia item with the full d01.txt. 2. Remove some PDF and HTML lines from d01.txt and re-run. 3. Remove one more PDF and one more HTML line and re-run. | Run 2/3: the removed documents = DISPLAY_ORDER.xlsx rows OPERATION DELETE, STATUS SUCCESS, remark 'VIEW CONTENT DELETED - DOCUMENT IS NOT IN THE DISPLAY ORDER FILE.'; log 'cleared by the document step and not re-created'; no view content rows left; they stay in the preview WITHOUT tree; documents dropped in an earlier run are not reported again. | MC Dev | - | High | Passed | MC Dev 5736-5741 | 2026-10-14 | familia NewM_familia_van_ncp WM FL0001: 5739 (option A war) reported SM231910, SM231920 (PDF) + SM231261 (HTML) as DELETE / SUCCESS ('cleared by the document step and not re-created'); 5740 / 5741 did not report them again (no view content left); preview after the revert shows dropped documents without tree. CD: no CD lines removed, 'all in the CD files'.
T38 | Conversion - view content status | MC | Listed but not converted document keeps its published view content status | New 2026-10-14: VC_CONTENT_STATUS follows the DMT document's published flag (ViewContentStatus) instead of always Draft. | 1. Publish a familia PDF document. 2. Remove its source file, keep its line in d01.txt, re-run the item. 3. Query gms3_vc_japan_vin_details for the document. | Document not in the preview, no DELETE row, INSERT SUCCESS in DISPLAY_ORDER.xlsx; its view content rows VC_CONTENT_STATUS = Published (Draft while it was unpublished). | MC Dev | - | High | Passed | MC Dev 5741 / 5742 / 5743 | 2026-10-14 | SM231917 (J_DTSNAMELIST_4.pdf, source removed, kept in d01.txt): 5741 view content Draft (unpublished); published by 5742 from 5739 (0.6 -> 1.0); 5743 re-run: not in preview, INSERT SUCCESS, view content 2 rows Published (user query).
T39 | Conversion - display order / CD cleanup + view content status | MME / MNAO | T37 + T38 for MME (view content + CD) and MNAO (view content model year + VIN, no CD) | Same code wired into StartMMEConversionImpl / StartConversionMNAOImpl and their DAOs; run on MC only (T37, T38). | As T37 and T38 with an MME and an MNAO item. | As T37 / T38 (MNAO: both gms3_vc_model_year_details and gms3_vc_vin_details). | MC Dev | T37, T38 | Medium | Passed | Accepted on the MC result (T37 / T38) | 2026-10-14 | Closed by the user without a separate run: MME and MNAO use the same shared code (UnlistedDisplayData, ClearedDisplayData, ViewContentStatus) - MC result accepted for both.

## Summary
Status | Count
Pending
In Progress
Passed
Failed
Blocked
Not Applicable
Total
Area | Open (not Passed / Not Applicable)
Master Data with Content
Schedule - Only content check
Conversion re-test
Conversion - ESI
Preview
Conversion - WD
Conversion - WM
History
File behaviour
Automation (Facelift)
QA regression
Schedule page
Regression
Schedule - Conversion Go
Conversion - display order file
Settings page
Conversion - library paths sent to Kapture
Conversion - display order / CD cleanup
Conversion - view content status
Conversion - display order / CD cleanup + view content status

## External Dependencies
ID | Owner | Item | What closes it | Status
E01 | Kapture | Bulk update rollbacks ('Plugin instructed the server to rollback') under load on MC Dev | Re-run of the affected items shows 0 rollbacks once Kapture deploys the fix. | Open
E02 | Kapture | 4 locked WD docs (aborted run 5511) + 11 PDFs refused | Re-run the MC item after Kapture clears them; docs created. | Open
E03 | Kapture | Publish ~6.9 s/doc, bulk update ~2.3 s/doc; is parallel publish safe? | Answer from Kapture; timing re-check if they change anything. | Open
E04 | Infra | rsync -> Syncthing on /s3kapture | Unblocks T14. | Open
E05 | Business data | ENT <Revision Year/Month/Day> tags malformed (SAX error in log, CX-5 ENTs) | Kept in the log on purpose as the marker; business fixes the tags. | Open
E06 | Business data | Voltage JS paths without FL folder; Hybrid carline KB*C3 vs KBAC3; ESI 409 names | Business corrects source content. | Open
E07 | Housekeeping | Test category ZZDUPTEST01 on SC Dev (42 rows) | Remove through the Kapture UI or Softclouds (no delete grant). | Open

## Open Decisions
ID | Decision | Current state
O7 | Sanitizer: generic (Job 10 rules) vs legacy per-process cleaning | Kept generic until decided.
D1-D8 | Automation decisions (publish state, Kapture read-back, DMT tables, vc_content_status, missing VIN category, channels, MNAO match, bulk) | DECIDED 2026-10-11 and built: published stays published, read latest + swap VIN categories only, DMT tables untouched, missing new VIN = validation error unless in the ALL_VIN file, legacy MNAO match, set-based SQL. Load type = option B (dc_load_type).
- | Optional: skip unchanged documents on re-run (content hash); reuse the Kapture login | User's call.

## Closed (reference)
Functionality | Market | Job IDs | Closed on
MC conversion + publish + delete | MC | 5546 / 5553 / 5595 / 5602 | 2026-10-05
MME conversion + publish | MME | 5603 / 5610 / 5617 | 2026-10-05
MNAO conversion + publish + delete | MNAO | 5673 / 5666 / 5680 | 2026-10-07
Master Data Syncing (InfoManager-free, DB mode, all-locales fill) | All | 899 / 906 / 913 | 2026-10-10
MNAO conversion re-test on the new war (Master Data with Content + Only content) | MNAO | 5687 / 5694 | 2026-10-10
Label rule aligned between both screens | MNAO | 5701 / 934 | 2026-10-10
D01 same refkey in two hierarchies - API = DB behaviour | MNAO | SC Dev API test | 2026-10-10
Meta Data Validation (all types, all markets) | All | 605-689 | 2026-10-11

## Legend
Status | Meaning
Pending | Not run yet
In Progress | Being run
Passed | Run, expected result seen - fill Job ID / Evidence + Tested on
Failed | Run, result differs - details in Remarks
Blocked | Cannot run until the 'Depends on' item is done
Not Applicable | Dropped by decision - reason in Remarks